## Gantt Chart
IS_10_Gantt Chart
PROJECT TITLE |  | Design and Performance Analysis of a Portable Multi-GPU Unit for Artificial Intelligence, Machine Learning, and Information Security |  |  |  |  | COMPANY NAME | [8 empty] | Professional Officers Division, SIT
PROJECT MANAGER |  | - |  |  |  |  | DATE | [8 empty] | 7/14/2021 - Updated
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [20 empty] | PHASE TWO | [34 empty] | PHASE THREE | [20 empty] | PHASE FOUR
[7 empty] | WEEK 1 (3rd May) | [6 empty] | WEEK 2 (10th May) | [6 empty] | WEEK 3 (17th May) | [6 empty] | WEEK 4 (24th May) | [6 empty] | WEEK 5 (31st May) | [6 empty] | WEEK 6 (7th June) | [6 empty] | WEEK 7 (14th June) | [6 empty] | WEEK 8 (21st June) | [6 empty] | WEEK 9 (28th June) | [6 empty] | WEEK 10 (5th July) | [6 empty] | WEEK 11 (12th July) | [6 empty] | WEEK 12 (19th July) | [6 empty] | WEEK 13 (26th July)
[7 empty] | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S
1 | Project Specification Phase
1.1 | Define project objectives | All | 2021-05-03 | 2021-05-03 | 1 | 100% | bar: WEEK 1 (3rd May) M
1.2 | Performance Benchmark Research | All | 2021-05-04 | 2021-05-08 | 5 | 100% | bar: WEEK 1 (3rd May) T to WEEK 1 (3rd May) S
1.2.1 | Hashcat | Chang Jie |  |  |  | 100% | bar: WEEK 1 (3rd May) T to WEEK 1 (3rd May) S
1.2.2 | AI-Benchmark | Nicholas & Chong Peng |  |  |  | 100% | bar: WEEK 1 (3rd May) T to WEEK 1 (3rd May) S
1.2.3 | PyTorch Benchmark | Azfar & Chang Jie |  |  |  | 100% | bar: WEEK 1 (3rd May) T to WEEK 1 (3rd May) S
1.2.4 | MLPerf Benchmarks | Nicholas & Chang Jie |  |  |  | 100% | bar: WEEK 1 (3rd May) T to WEEK 1 (3rd May) S
1.2.5 | DeepBench | Azfar |  |  |  | 100% | bar: WEEK 1 (3rd May) T to WEEK 1 (3rd May) S
1.2.6 | DAWNBench | Chang Jie |  |  |  | 100% | bar: WEEK 1 (3rd May) T to WEEK 1 (3rd May) S
1.2.7 | Lambda Labs Benchmark | Chong Peng |  |  |  | 100% | bar: WEEK 1 (3rd May) T to WEEK 1 (3rd May) S
1.3 | Testing of Benchmarks | All | 2021-05-09 | 2021-05-15 | 7 | 100% | bar: WEEK 1 (3rd May) S to WEEK 2 (10th May) S
1.4 | Define Project Plan | Nicholas & Chong Peng & Chang Jie | 2021-05-16 | 2021-05-19 | 4 | 100% | bar: WEEK 2 (10th May) S to WEEK 3 (17th May) W
1.5 | Gantt Chart | Azfar | 2021-05-16 | 2021-05-19 | 4 | 100% | bar: WEEK 2 (10th May) S to WEEK 3 (17th May) W
1.6 | Create Report | Chang Jie | 2021-05-20 | 2021-05-23 | 4 | 100% | bar: WEEK 3 (17th May) R to WEEK 3 (17th May) S
2 | Implementation Phase
2.1 | IS Report Writeup | All | 2021-05-24 | 2021-06-04 | 12 | 100% | bar: WEEK 4 (24th May) M to WEEK 5 (31st May) F
2.2 | Midway Reflective Report | Individual | 2021-06-05 | 2021-06-08 | 4 | 100% | bar: WEEK 5 (31st May) S to WEEK 6 (7th June) T
2.3 | Define Test Cases (Setups A, B, C) | All | 2021-06-09 | 2021-06-13 | 5 | 100% | bar: WEEK 6 (7th June) W to WEEK 6 (7th June) S
2.4 | Environment Setup | All | 2021-06-14 | 2021-06-16 | 3 | 100% | bar: WEEK 7 (14th June) M to WEEK 7 (14th June) W
2.5 | Run Benchmarks (Setup A) | All | 2021-06-16 | 2021-07-06 | 21 | 100% | bar: WEEK 7 (14th June) W to WEEK 10 (5th July) T
2.5.1 | Hashcat |  | 2021-06-16 | 2021-06-17 | 2 | 100% | bar: WEEK 7 (14th June) W to WEEK 7 (14th June) R
2.5.2 | HPLinpack |  | 2021-06-18 | 2021-06-19 | 2 | 100% | bar: WEEK 7 (14th June) F to WEEK 7 (14th June) S
2.5.3 | DLRM (MLPerf) |  | 2021-06-20 | 2021-06-22 | 3 | 0% | bar: WEEK 7 (14th June) S to WEEK 8 (21st June) T
2.5.4 | Lambda Labs Benchmark |  | 2021-06-22 | 2021-06-25 | 4 | 0% | bar: WEEK 8 (21st June) T to WEEK 8 (21st June) F
2.5.5 | SSD (MLPerf) |  | 2021-06-25 | 2021-06-27 | 3 | 100% | bar: WEEK 8 (21st June) F to WEEK 8 (21st June) S
2.5.6 | GNMT (MLPerf) |  | 2021-06-28 | 2021-06-29 | 2 | 0% | bar: WEEK 9 (28th June) M to WEEK 9 (28th June) T
2.5.7 | Mask R-CNN (MLPerf) |  | 2021-06-29 | 2021-06-30 | 2 | 100% | bar: WEEK 9 (28th June) T to WEEK 9 (28th June) W
2.5.9 | Transformer (MLPerf) |  | 2021-06-30 | 2021-07-02 | 3 | 0% | bar: WEEK 9 (28th June) R to WEEK 9 (28th June) F
2.5.10 | ResNet-50 (MLPerf) |  | 2021-07-02 | 2021-07-03 | 2 | 100% | bar: WEEK 9 (28th June) F to WEEK 9 (28th June) S
2.5.11 | MiniGo (MLPerf) |  | 2021-07-03 | 2021-07-05 | 3 | 100% | bar: WEEK 9 (28th June) S to WEEK 10 (5th July) M
2.5.12 | BERT (MLPerf) |  | 2021-07-05 | 2021-07-06 | 2 | 0% | bar: WEEK 10 (5th July) M to WEEK 10 (5th July) T
2.6 | Run Benchmarks (Setup B) | Nicholas & Chong Peng | 2021-07-06 | 2021-07-12 | 7 | 100% | bar: WEEK 10 (5th July) T to WEEK 11 (12th July) M
2.6.1 | Hashcat |  | 2021-07-06 | 2021-07-07 | 2 | 100% | bar: WEEK 10 (5th July) T to WEEK 10 (5th July) W
2.6.2 | HPLinpack |  | 2021-07-08 | 2021-07-09 | 2 | 100% | bar: WEEK 10 (5th July) R to WEEK 10 (5th July) F
2.6.3 | SSD |  | 2021-07-09 | 2021-07-10 | 2 | 100% | bar: WEEK 10 (5th July) F to WEEK 10 (5th July) S
2.6.4 | ResNet-50 |  | 2021-07-11 | 2021-07-12 | 2 | 100% | bar: WEEK 10 (5th July) S to WEEK 11 (12th July) M
2.7 | Run Benchmarks (Setup C) | Nicholas & Chong Peng | 2021-07-13 | 2021-07-19 | 7 | 100% | bar: WEEK 11 (12th July) T to WEEK 12 (19th July) M
2.7.1 | Hashcat |  | 2021-07-13 | 2021-07-14 | 2 | 100% | bar: WEEK 11 (12th July) T to WEEK 11 (12th July) W
2.7.2 | HPLinpack |  | 2021-07-14 | 2021-07-14 | 1 | 100% | bar: WEEK 11 (12th July) W
2.7.3 | ResNet-50 |  | 2021-07-14 | 2021-07-16 | 3 | 100% | bar: WEEK 11 (12th July) W to WEEK 11 (12th July) F
2.7.4 | SSD |  | 2021-07-16 | 2021-07-19 | 4 | 100% | bar: WEEK 11 (12th July) F to WEEK 12 (19th July) M
2.6 | Data Collection | All | 2021-06-16 | 2021-07-19 | 34 | 100% | bar: WEEK 7 (14th June) W to WEEK 12 (19th July) M
2.7 | Update Report & Project Plan | All | 2021-06-18 | 2021-07-21 | 34 | 100% | bar: WEEK 7 (14th June) F to WEEK 12 (19th July) W
2.8 | Update Gantt Chart | Azfar | 2021-06-06 | 2021-07-09 | 4 | 100% | bar: WEEK 10 (5th July) T to WEEK 10 (5th July) F
3 | Analysis Phase
3.1 | Data Analysis & Comparison | All | 2021-07-07 | 2021-07-21 | 15 | 100% | bar: WEEK 10 (5th July) W to WEEK 12 (19th July) W
4 | Submission Phase
4.1 | Create Poster & Video | Nicholas | 2021-07-12 | 2021-07-21 | 10 | 100% | bar: WEEK 11 (12th July) M to WEEK 12 (19th July) W
4.2 | Create Presentation Slides | Azfar | 2021-07-12 | 2021-07-21 | 10 | 100% | bar: WEEK 11 (12th July) M to WEEK 12 (19th July) W
4.3 | Finalize Best Environment Setup | All | 2021-07-19 | 2021-07-23 | 5 | 100% | bar: WEEK 12 (19th July) M to WEEK 12 (19th July) F
4.4 | Create Academic Paper | All | 2021-07-19 | 2021-07-30 | 12 | 100% | bar: WEEK 12 (19th July) M to WEEK 13 (26th July) F
4.5 | Complete Final Report | All | 2021-07-26 | 2021-07-30 | 5 | 100% | bar: WEEK 13 (26th July) M to WEEK 13 (26th July) F
4.6 | Final Reflective Report | Individual | 2021-07-29 | 2021-07-30 | 2 | 100% | bar: WEEK 13 (26th July) R to WEEK 13 (26th July) F